## Stakeholder Registry
Project Name: Project Stakeholder Registry | Sun room on Kelly’s personal home
Stakeholder Name or Group | Priority Key - Secondary - Other | Requirements, Needs, Wants | Power Ability to stop or change the project | Interest in Project Comparison between their interest and the project goals | Advocate or Adversary | Engagement Strategy
Allyson Kelly - Owner | Key | Budget, quality, flexibility | High - can stop or change the project | High - Must be done with high standards | Advocate | Listen to concerns, communication
HOA group - Leaders | Secondary | Appearance, rules followed | High - can stop or change the project | High - Must follow CCR guidance | Adversary | Show them plans to get their approval
County inspector | Key | Project adheres to regulations | High - can stop or change the project | Medium - as long as regulations are followed | Adversary | Connect when inspector on site
Architect | Key | Project is built to spec | High - can stop or change the project | High - this may affect their reputation | Advocate | Connect as needed for success
Lead Carpenter | Key | A good architecture plan that follows modern building standards. Can suggest changes to save money or assembly the room in a more efficient way. Good sub contractors. Good relationship with stakeholders. | High - can stop or change the project | Medium - changes should be kept to a minimum | Advocate | Good communication, connect face to face.
Master Electrician | Secondary | Architect plan is built to code | Low, follows plan | Low, just doing a contract job | Advocate | Good communication, connect face to face.
Lead Plumber | Secondary | Architect plan is built to code | Low, follows plan | Low, just doing a contract job | Advocate | Good communication, connect face to face.
Before you dig team | Other | Location of foundation | Medium, can change or adjust plan | Low, just identifying wires and pipes in ground | Advocate | Good communication, connect face to face.
Concrete Company | Other | Access to site | Low, will workaround access issues | Medium, forms for concrete must be built correctly. | Advocate | Good communication, connect face to face.
Note: Project Sponsor, and team members are considered stakeholders
There may need to be some speculation for completing the Stakeholder Registry

## Communications Matrix
Project Name: Sun room on Kelly’s personal home | Project Stakeholder Communication Matrix
Stakeholder Name or Group | Purposes Project Info Needs | Methods | Timing/Frequency
Allyson Kelly | Direction Setting, Change Control, Status Reporting, Approval of testing or other outputs, Authorization | Verbal communication - face to face, texting or email for documentation | Daily if work is done on that day
HOA group | Status Reporting, Approval of testing or other outputs, Information Seeking | email | Weekly updates
County inspector | Authorization, Information Seeking | Call, email | Update as needed when an item needs inspection
Architect | Direction Setting, Status Reporting, Change Control,Lessons Learned | Text or email | Update as needed when an item needs changing and affect the architecture plan
Lead Carpenter | Change Control, Approval of testing or other outputs, Direction Setting | Call, Text or email | Daily if work is done on that day
Master Electrician | Approval of testing or other outputs | Call or email | Daily if work is done on that day
Lead Plumber | Approval of testing or other outputs | Call or email | Daily if work is done on that day
Before you dig team | Approval of testing or other outputs | Call or email | Daily if work is done on that day
Concrete Company | Approval of testing or other outputs | Call or email | Daily if work is done on that day
Note: Project Sponsor, and team members are considered stakeholders
There may need to be some speculation for completing the Communications Matrix

## Academic Integrity Statement
Academic Integrity Statement
We commit ourselves to Washington State University's high standards to uphold academic honesty and scholarly values as established by the WSU's Standards of Conduct. We affirm that we have not given or received any unauthorized assistance on this assignment/examination, that the work product presented here is the work of the author(s) [all team members listed], and that all materials from other sources (including books, articles, Internet, or other media), whether quoted or paraphrased, have been properly cited. David Kelly (Typing our names above serves as our signatures.)