## Work Breakdown Structure
NOTE: To add a new row to the table below, place the cursor in the bottom-right cell of the table and press "Tab"
Item Code | Name | Work to be Completed | Assigned To | Resources Needed | Resource Unit Cost(s) | Duration
1 | Project Start
1.1 | Architect Meeting | Create building plan | Architect, PM, Owner | Plans needed for Inspector and Lead Carpenter | 5000 | 20 days
1.2 | Permits | Get the approval of the County inspector | Architect, PM, Owner | Approved plans | 1000 | 15 days
1.3 | HOA Approval | Get the HOA boards approval | PM, Owner | Email or letter approval | 0 | 10 days
1.4 | Before You Dig Approval | Utility companies ID wire or pipes under site area | 811, utility companies | Paint, locator device | 0 | 8 days
2 | Area preparation
2.1 | Clear debris | Remove shrubs and level area | PM, Owner | Cutters, shovel, rake | 0 | 1 day
2.2 | Foundation prep | Stake, level, dig for foundation | Lead Carpenter | Front loader/backhoe | 1500 | 1 day
3 | Foundation
3.1 | Build forms | Construct forms per plans | Lead Carpenter | Forms, rebar | 1500 | 1 day
3.2 | Poor Concrete | Concrete company to fill forms | Concrete Company, Lead Carpenter |  | 2000 | .5 day
3.3 | Finish Concrete | Set anchor bolts, finish top and edges of foundation | Lead Carpenter | Anchor bolts | 500 | .5 day
4 | Framing
4.1 | Floor joists | Install top plate and joists per plans | Lead Carpenter | 2x6 and 2x12 lumber, hangers | 3000 | 3 days
4.2 | Insulate floor | Install insulation in floor per plans | Lead Carpenter | Insulation | 750 | 1 day
4.3 | Sub Floor | Install subfloor per plans | Lead Carpenter | 4x8 sheets of plywood | 1000 | 1 day
4.4 | Walls | Install walls per plans | Lead Carpenter | 2x4 lumber | 1500 | 2 days
4.5 | Roof trussess | Install trusses per plans | Lead Carpenter | Roof trusses (prefab) | 2500 | 1 day
5 | Windows
6.1 | Install room windows | Install room windows per plans | Lead Carpenter | Windows | 5500 | 2 days
6.2 | Install Skylights | Install roof shingles per plans | Lead Carpenter | Skylights | 2500 | 1 day
6 | Roof
5.1 | Install Roof boards | Install roof boards per plans | Lead Carpenter | 1x4 lumber | 600 | .5 days
5.2 | Install Roof shingles | Install roof shingles per plans | Lead Carpenter | Tar paper, cedar shingles | 2500 | 2 days
7 | Doors
7.1 | Install internal double door | Install double doors per plans | Lead Carpenter | Double doors, hardware | 2000 | 1 day
7.2 | Install single external door | Install single door per plans | Lead Carpenter | External door, hardware | 500 | .25 day
8 | Siding
8.1 | Install exterior Sheathing | Install OSB Sheathing per plans | Lead Carpenter | 19/32 sheathing | 700 | 1 day
8.2 | Install exterior siding | Install ext siding per plans | Lead Carpenter | James Hardie siding | 1700 | 1 day
8.3 | Paint siding | Paint siding per plans | Owner | Exterior paint | 500 | 2 days
9 | Electrical
9.1 | Add electrical wire | Run new wires per plans | Electrician | Wire | 1350 | 1 day
9.2 | Add electrical components | Install lights boxes, switches boxes, outlets per plans | Electrician | electrical boxes, switches, outlets | 1000 | 1 day
10 | Wall finishing
10.1 | Install Sheetrock | Install sheetrock per plans | Lead Carpenter | Sheetrock | 1000 | 2 days
10.2 | Plaster wall | Plaster walls per plans | Lead Carpenter | Plaster | 500 | 1 day
10.3 | Paint walls | Paint walls per plans | Owner | Paint | 200 | 1 day
10.4 | Install lights and elec components | Install lights, switch covers, outlet covers per plans | Lead Carpenter | covers, lights | 500 | 1 day
11 | Floor
11.1 | Install flooring | Install flooring per plans | Lead Carpenter | New flooring | 1000 | 1 day
11.2 | Install base boards | Install baseboards per plans | Lead Carpenter | Baseboard wood | 200 | .25 day
12 | Plumber
12.1 | Install pipe | Install pipe for fireplace per plans | Plumber | Pipe | 1000 | .5 day
12.2 | Install ducting and vents | Install ducting for HVAC per plans | Plumber | Duct, vents | 1000 | .5 day
12.3 | Install Fireplace | Install fireplace per plans | Plumber | Fireplace | 4500 | 1 day
13 | Window Blinds
13.1 | Install Window blinds | Install window blinds per plans | Owner | Window blinds | 1000 | 2 days
14 | Exterior
14.1 | Clean up area | Clean up area | Owner | NA | 0 | .5 day
14.2 | Install gutters | Install gutter and drain spouts per plans | Lead Carpenter | Gutters, pipes | 500 | 1 day
14.3 | Install facia | Install Facia per plans | Lead Carpenter | Trim boards | 500 | 1 day
15 | Project End
15.1 | Final county inspection | Inspection | County Inspector | NA | 500 | .25 day
|  |  |  | Total | 51500

## Academic Integrity Statement
Academic Integrity Statement
I commit myself to Washington State University's high standards to uphold academic honesty and scholarly values as established by the WSU's Standards of Conduct. I affirm that I have not given or received any unauthorized assistance on this assignment/examination, that the work product presented here is the work of the author(s) [all team members listed], and that all materials from other sources (including books, articles, Internet, or other media), whether quoted or paraphrased, have been properly cited.
David Kelly