## Risk Registry
Risk Assessment | [5 empty] | Risk Mitigation
Risk ID | Risk Event | Description | Likelihood/ Probability 1-5 | Impact 1-5 | Score Likelihood X Impact | Trigger | Response | Responsibility/Assigned | Comments
1 | Get plans approved | County does not approve plans | 2 | 3 | 6 | The approval process takes longer than normal | Call the County to get a status | Project Manager | Expect 10 days or more
2 | Get plans approved | HOA does not approve plans | 1 | 3 | 3 | The approval process takes longer than normal | Call the HOA to get a status | Project Manager | Expect 5 days or more
3 | Rainy weather | The rain could damage partially built room | 3 | 3 | 9 | Bad weather is coming | Purchase tarps to cover the site | Project Manager | Could return them if not needed
4 | Underground utilities | Pipes and wires are under new room | 1 | 4 | 4 | The owner does not have good drawings of utility locations | Delay digging the foundation and estimate moving utilities | Project Manager/Carpenter
5 | Carpenter resources | Carpenter resources are limited in current time | 3 | 5 | 15 | Home building and remodels are vigorous at this time | Get committed resources early | Project Manager
6 | Framing Inspection | Framing fails inspection | 2 | 3 | 6 | Carpenters are inexperienced | Connect with Lead carpenter frequently | Project Manager
7 | Costs of materials | Cost of materials is 30% higher than last year | 4 | 3 | 12 | Prices are rising compared to last year | Look for alternative materials | Project Manager/Carpenter | Can we use used materials?
8 | Cedar shingle shortage | Delay in getting cedar shingles for roof | 4 | 1 | 4 | Washington no longer sells cedar shingles | Buy them from Canada at a premium | Project Manager/Carpenter | Buy from another state?
9 | Sink holes | Soil under room is a sink hole | 2 | 5 | 10 | There is another sink hole close to the project area | Drive spikes into ground to test it. Mitigate if found. | Owner
10 | Price increase | Actual price is higher that estimate | 3 | 3 | 9 | The first material purchase is over budget | Analyze why the price is higher | Project Manager
11 | Concrete failure | Concrete dries before bolts are installed | 2 | 3 | 6 | The day of the pour is very hot | Ask the cement company to add more water | Carpenter - Lead
12 | Window issue | The windows might be too dark to see the views | 2 | 3 | 6 | The Visible Transmittance number was not requested in the order | Call the window company to verify the number to be about .5 | Project Manager
Academic Integrity Statement
I commit myself to Washington State University's high standards to uphold academic honesty and scholarly values as established by the WSU's Standards of Conduct. I affirm that I have not given or received any unauthorized assistance on this assignment/examination, that the work product presented here is the work of the author(s) [all team members listed], and that all materials from other sources (including books, articles, Internet, or other media), whether quoted or paraphrased, have been properly cited.
David Kelly